## OPL
Open Points List (OPL) | [9 empty] | no macro version
Title: |  | My OPL, My Project |  | http://www.excelmadeeasy.com/ | [13 empty] | Task Count
| Owner: | Your Name |  | Date: | 2014-11-01 | [7 empty] | Data for statistics - automatically updated |  |  |  |  | 13
No. | Task Creation Date | product | Subject | Action Item | Resp | Planned finish date | Status | Actual finish date | Estimated Completion Time (days) | Result | Information, Escalation, Feedback | Priority | Completion month | Completed on time | Completed overdue | Days overdue | Telecon
1 | 2014-02-01 | no1 | create OPL | Use this OPL every day of my life. Yes you should use it everyday of your life | myself | 2014-04-01 | completed | 2014-03-31 | 5 | none yet, but we are waiting for more news from the customer |  |  | 2014-03-01 | 1 | 0 | 0
2 | 2014-04-13 | no2 | create OPL | Use this OPL every day of my life | myself | 1/102014 | reminder |  |  |  |  | 1 |  | 0 | 0
3 | 2008-04-13 | no3 | create OPL | Use this OPL every day of my life | myself | 2014-04-19 | _overdue |  |  |  |  | 2 |  | 0 | 0
4 | 2014-01-01 | no4 | create OPL | Use this OPL every day of my life | myself | 2014-02-01 | completed | 2014-03-15 |  |  |  | 1 | 2014-03-01 | 0 | 1 | 44
5 | 2014-01-02 | no5 | create OPL | Use this OPL every day of my life | Laura | 2014-12-01 | _LATE |  | 40 |  |  | 2 |  | 0 | 0
6 | 2014-04-13 | no6 | create OPL | Use this OPL every day of my life | you | 2014-05-15 | completed | 2014-01-05 |  |  |  | 1 | 2014-01-01 | 1 | 0 | 0
7 | 2014-11-01 | test | test | test | john | 2014-11-03 | warning |  |  |  |  | 1 |  | 0 | 0
8 | 2014-11-01 | test2 | test2 | test2 | Laura | 2014-09-05 | _overdue |  |  |  |  | 2 |  | 0 | 0
9 | 2014-11-01 | test3 | test3 | test3 | Lana | 2014-11-15 | new | [6 empty] | 0 | 0
10 | 2014-11-01 |  |  |  |  | 2014-11-01 | warning | [6 empty] | 0 | 0
11 | 2014-11-01 |  |  |  |  | 2014-11-01 | warning | [6 empty] | 0 | 0
12 | 2014-11-01 | [12 empty] | 0 | 0
13 | 2014-11-01 | [12 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
[14 empty] | 0 | 0
| Do not add any thing under this line. Use COPY and INSERT COPIED CELL on the place where you want to insert a new line. If you just INSERT new line, you will not copy the formulas. | [10 empty] | last
Formulas:
Status = IF([Title:]<>"",IF([Actual finish date]<>"","completed",IF([Planned finish date]<TODAY(),"_overdue",IF([Planned finish date]<TODAY()+[Estimated Completion Time (days)]*1.4, "_LATE",IF([Planned finish date]<TODAY()+7+[Estimated Completion Time (days)]*1.4,"warning",IF([Task Creation Date]<TODAY()-7,"reminder","new"))))),"")
Completion month = IF([Actual finish date]<>"",DATE(YEAR([Actual finish date]),MONTH([Actual finish date]),1),"")
Note on A4: Running number
Note on B4: Date on which the task has been defined (day/month/year)
Note on C4: This number is linked to the Ref No column in worksheet "Cateogry - Tasks" and can be used to categorise parts
Note on E4: List the results of an action (date when that information became available) [day / month/ year]
Note on F4: One person must be responsible only
Note on G4: Date on which the task has to be completed (day/month/year)
Note on H4: Automatically filled: Caution: overdue in 1 week Pending: overdue in more than 1 week Overdue: due date over Closed: task closed New: new task, which has to be closed in more than 1 week
Note on I4: Indicate the date on which the task has been closed (day/month/year)
Note on J4: Enter the estimated time to complete the task.
Note on L4: indicate names of persons who should be directly informed about the task results, or to whom the task must be escalated to if deadline is in risk
Note on M4: A = URGENT B = high C = normal

## meeting participants
http://www.excelmadeeasy.com/
Enter the date of the meeting so you can track who came
shortname | PRESENCE | 2014-11-01 | 2014-11-08 | 2014-11-15 | 2014-11-22 | 2014-11-29 | 2014-12-06 | 2014-12-13 | 2014-12-20 | 2014-12-27 | 2015-01-03 | 2015-01-10
for tasks
| Name 1 | x
| Name 2 |  | x
| Name 3 | x
| Name 4 | x
| Name 5 | x
| Name 6 | x
| Name 7 | x
| Name 8 | x
| Name 9 | x | x
| Name 10 |  | x
| Name 11 | x
| Name 12 | x | x
| Name 13 | x | x
| Name 14 | x | x

## Compl - by overdue
Closed tasks, by overdue status
[5 empty] | Title: | 0
http://www.excelmadeeasy.com/
Closed tasks, by overdue status
Status |  |  |  | Number of tasks |  |  | Month | Tasks completed
on time |  |  |  | 2 |  |  |  | On-time | Overdue
0 | to | 1 | weeks | 0 |  |  | 2014-01-01 | 1 | 0
1 | to | 2 | weeks | 0 |  |  | 2014-02-01 | 0 | 0
2 | to | 3 | weeks | 0 |  |  | 2014-03-01 | 1 | 1
3 | to | 4 | weeks | 0 |  |  | 2014-04-01 | 0 | 0
4 | to | 5 | weeks | 0 |  |  | 2014-05-01 | 0 | 0
5 | to | 6 | weeks | 0 |  |  | 2014-06-01 | 0 | 0
6 | to | 7 | weeks | 0 |  |  | 2014-07-01 | 0 | 0
7 | to | 8 | weeks | 0 |  |  | 2014-08-01 | 0 | 0
8 | to | 9 | weeks | 1 |  |  | 2014-09-01 | 0 | 0
9 | or more |  | weeks | 0 |  |  | 2014-10-01 | 0 | 0
[7 empty] | 2014-11-01 | 0 | 1
[7 empty] | 2014-12-01 | 0 | 0
Update the months in this table to the year you are working.

## By Resp - Status
|  |  |  | [Insert project/purpose name here] |  |  |  | http://www.excelmadeeasy.com/
Task Status by Responsibility
Overview of task status by responsibility
Planned Deadlines | Status
Resp | completed | _overdue | warning | reminder | _LATE | new | Grand Total
you | 1 | 0 | 0 | 0 | 0 | 0 | 1
myself | 2 | 1 | 0 | 1 | 0 | 0 | 4
john | 0 | 0 | 1 | 0 | 0 | 0 | 1
Laura | 0 | 1 | 0 | 0 | 1 | 0 | 2
Lana | 0 | 0 | 0 | 0 | 0 | 1 | 1
Grand Total | 3 | 2 | 1 | 1 | 1 | 1 | 9
Note on K11: to update the table: select the cell "Planned Deadlines" with the mouse, click the right buttom and select "Refresh Data"
Click in the table and press ALT-F5 to refresh it.

## Category - Tasks
List of tasks categories/working departments and their unique ID number
50
| Ref No | Abbreviations | Designation/ Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Achtung! Für weitere Arbeitspakete muss Makro geändert werden:
=> Formulare > "Auswahl_HAP"
=> Private Sub UserForm_Initialize => Range ändern (Default D53, 1. Zeile in Subrutine)

## By Category - Status
Closed tasks, by overdue status
[5 empty] | Title: | 0
Count of Planned finish date | Status
| completed | (blank) |  | _overdue | reminder | warning | _LATE | new | Grand Total
Total | 3 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 9

## How to Use
How to use the Open Points List | http://www.excelmadeeasy.com/
Purpose: It is envisaged that an open points list can be used to track tasks common to a Department, Section, Project, Topic.
Usage:
1. Fill out the fields on the sheet "OPL" according to the comments on each column heading. To do this hold the mouse over the coloumn heading.
2. To use Pivot Tables and Graphs right click on field and select refresh data. The graphs will be empty until your open points list contains data.
3. Task Categories
If you define task catergories in the worksheet "Category - Tasks" you can refer to them by their Ref. No. in the main OPL list. This data is used to create the graph of tasks by category too in the worksheet "By Category - Status"
How Status field works.
If you wish to know what criteria are used for the status field, the following flowchart details the decisions the spreadsheet makes.