## Basic Data input
Welcome to the Excel Made Easy Gantt Chart project management Tool.
This is the light version. The pro version can be downloaded from
http://www.excelmadeeasy.com/professional-project-management.php
Terms of use under Licence, terms of use tab or under this link.
http://www.excelmadeeasy.com/pjm_term_of_use.php
INPUT SHEET (enter these basic informations about your project, will be copied automatically to the project)
Project Name | Enter name in basic data input
Project Manager Name | Joe PJM
Start Date | 2014-12-01
What is the first day of the week
Sunday=1, Monday=2 | 2 | Monday
Enter the Holidays in the holidays Tab | (Pro version feature)
Explanations: |  |  | Online Help press here
Use the Gantt Chart Workdays (pro version) to enter durations in workdays or use the Gantt Chart Calendar days to enter durations in calendars days (includes holidays)
You need to install the Analysis ToolPak. In Options, Add-ins and select the Analysis ToolPak
Only type in the Green cells.
The slider allows to change the display of the gantt chart. Moves by one days (click on arrow) or one month (click on grey area)
You can enter the start date of the display in the cell just over the slider
Holidays (pro version)
Enter the Holidays in the holidays Tab |  | (Pro version feature) |  | The basic version only has Saturdays and Sundays as non working days
Following Task (free and pro version)
To have one task follow another type in the START date of the task =Workday(enddate,1)
Grouping of Task (pro version)
Use the grouping function under the Ribbon DATA and in the group section (pro version)
Change colors (pro version)
Go into the conditional formating. Be sure to select whole worksheet and change the color by double click on the format tab (pro version)
Adding/inserting new task (free and pro version)
Copy from the template at the bottom and then insert it where you want by right click on the row and insert copied cells
Beware to update the formulas in STARTDAY, DURATION and PERCENTAGE COMPLETION in the top task when inserting new tasks. These are the ones to look at.
You must make sure the range is including all subtasks.
Print
Select the area you want to print and in the print menu select print selection
The orange line is today's date
Always keep the WBS column uninterrupted to keep the automatic numbering.
duration for any task subtask etc... is
max(enc date of the subtasks) - start date + 1
e.g.:=MAX(F9:F14)-E8+1
Start date for any task is the
min(all subtasks)
eg: =MIN(E20:E26)
End date: is the start date + duration - 1
e.g.:=E38+G38-1
Percentage completed of a task
=SUMPRODUCT(duration of subtasks;percentages of subtask)/SUM(duration of subtasks)
eg:=SUMPRODUCT(G39:G41;H39:H41)/SUM(G39:G41)

## Gant Chart Calendar Days
Enter name in basic data input | [60 empty] | To unlock this spreadsheet, purchase the Professional Version from: | [122 empty] | You can also use our free task list to follow up on the project items. | [57 empty] | Start of Gantt: | 0
Project Manager: |  | Joe PJM |  |  | Today's Date: |  |  | 2016-02-09 | [30 empty] | http://www.excelmadeeasy.com/professional-project-management.php | [203 empty] | 41974
Project start Date: |  | 2014-12-01 |  |  |  | (indicated by red line) |  |  | dddd | [233 empty] | 42399
[11 empty] | Start of graph: | [32 empty] | 2016-01-30 | [198 empty] | 425
60
[42] | time axis 2016-01-25 to 2016-09-11
WBS | Task name | Responsible | Week day | Start day | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2016-01-25: 2016-01-25; 2016-02-01: 2016-02-01; 2016-02-08: 2016-02-08; 2016-02-15: 2016-02-15; 2016-02-22: 2016-02-22; 2016-02-29: 2016-02-29; 2016-03-07: 2016-03-07; 2016-03-14: 2016-03-14; 2016-03-21: 2016-03-21; 2016-03-28: 2016-03-28; 2016-04-04: 2016-04-04; 2016-04-11: 2016-04-11; 2016-04-18: 2016-04-18; 2016-04-25: 2016-04-25; 2016-05-02: 2016-05-02; 2016-05-09: 2016-05-09; 2016-05-16: 2016-05-16; 2016-05-23: 2016-05-23; 2016-05-30: 2016-05-30; 2016-06-06: 2016-06-06; 2016-06-13: 2016-06-13; 2016-06-20: 2016-06-20; 2016-06-27: 2016-06-27; 2016-07-04: 2016-07-04; 2016-07-11: 2016-07-11; 2016-07-18: 2016-07-18; 2016-07-25: 2016-07-25; 2016-08-01: 2016-08-01; 2016-08-08: 2016-08-08; 2016-08-15: 2016-08-15; 2016-08-22: 2016-08-22; 2016-08-29: 2016-08-29; 2016-09-05: 2016-09-05
1 | Task 1 | Name | 2016-02-09 | 2016-02-09 | 2016-05-12 | 94 | 38.39% | 68 | 36 | 58
1.1 | Sub Task 1.1 |  | 2016-02-09 | 2016-02-09 | 2016-03-29 | 50 | 50% | 36 | 25 | 25
1.2 | Sub Task 1.2 |  | 2016-03-30 | 2016-03-30 | 2016-04-28 | 30 | 50% | 22 | 15 | 15
1.2.1 | Sub Task 1.2.1 |  | 2016-03-30 | 2016-03-30 | 2016-04-18 | 20 | 0% | 14 | 0 | 20
1.2.2 | Sub Taks 1.2.2 |  | 2016-04-19 | 2016-04-19 | 2016-04-28 | 10 | 0% | 8 | 0 | 10
1.3 | Sub Task 1.3 |  | 2016-04-29 | 2016-04-29 | 2016-04-30 | 2 | 50% | 1 | 1 | 1
1.4 | Sub Task 1.4 |  | 2016-05-01 | 2016-05-01 | 2016-05-12 | 12 | 55% | 9 | 6 | 6
2 | Task 2 | Name | 2016-02-09 | 2016-02-09 | 2016-02-26 | 18 | 25% | 14 | 4 | 14
2.1 | Sub Task 2.1 |  | 2016-02-09 | 2016-02-09 | 2016-02-13 | 5 | 25% | 4 | 1 | 4
2.2 | Sub Task 2.2 |  | 2016-02-16 | 2016-02-16 | 2016-02-20 | 5 | 25% | 4 | 1 | 4
2.3 | Sub Task 2.3 |  | 2016-02-22 | 2016-02-22 | 2016-02-26 | 5 | 25% | 5 | 1 | 4
3 | Task 3 | Name | 2016-02-11 | 2016-02-11 | 2016-04-08 | 58 | 42.31% | 42 | 24 | 34
3.1 | Sub task 1.1 |  | 2016-02-11 | 2016-02-11 | 2016-02-20 | 10 | 0% | 7 | 0 | 10
3.2 | Sub Task 3.1 |  | 2016-02-21 | 2016-02-21 | 2016-02-26 | 6 | 100% | 5 | 6 | 0
3.3 | Sub Task 3.2 |  | 2016-02-27 | 2016-02-27 | 2016-03-27 | 30 | 50% | 20 | 15 | 15
3.3.1 | Sub Task 3.2.1 |  | 2016-02-11 | 2016-02-27 | 2016-03-12 | 15 | 20% | 11 | 3 | 12
3.3.2 | Sub Task 3.2.2 |  | 2016-02-11 | 2016-03-13 | 2016-03-27 | 15 | 20% | 11 | 3 | 12
3.4 | Sub Task 3.3 |  | 2016-03-28 | 2016-03-28 | 2016-04-02 | 6 | 50% | 5 | 3 | 3
3.5 | Sub Task 3.4 |  | 2016-04-03 | 2016-04-03 | 2016-04-08 | 6 | 50% | 5 | 3 | 3
4 | Task 4 | Name | 2016-02-09 | 2016-02-09 | 2016-03-01 | 22 | 0% | 16 | 0 | 22
4.1 | Sub Task 4.1 |  | 2016-02-09 | 2016-02-09 | 2016-02-13 | 5 | 0% | 4 | 0 | 5
4.2 | Sub Task 4.2 |  | 2016-02-16 | 2016-02-16 | 2016-02-20 | 5 | 0% | 4 | 0 | 5
4.3 | Sub Task 4.3 |  | 2016-02-21 | 2016-02-21 | 2016-02-25 | 5 | 0% | 4 | 0 | 5
4.4 | Sub Task 4.4 |  | 2016-02-26 | 2016-02-26 | 2016-03-01 | 5 | 0% | 3 | 0 | 5
Do not add any thing under this line. Use the insert row function before reaching this line. | bar: 2016-01-25 to 2016-01-29
TEMPLATE ROWS: Copy and insert the entire section, or just the specific sub tasks, depending on which level you want to use (formulas are different for different WBS levels)
Beware that the formula for STARTDAY, DURATION and PERCENTAGE COMPLETION must be updated
1 | Task 1 |  | 2016-02-11 | 2016-02-11 | 2016-03-01 | 20 | 6.667% | 14 | 1 | 19
1.1 | Sub task 1.1 |  | 2016-02-11 | 2016-02-11 | 2016-02-20 | 10 | 0% | 7 | 0 | 10
1.1.1 | Sub Task 1.1.1 |  | 2016-02-11 | 2016-02-11 | 2016-02-25 | 15 | 20% | 11 | 3 | 12
1.1.1.1 | Sub Task 1.1.1.1 |  | 2016-02-11 | 2016-02-11 | 2016-03-01 | 20 | 0% | 14 | 0 | 20
Note on M4: You can enter the first date of the graph here. If you delete it, it will use the slider or the project start date. Pro Version only
Note on A7: Work Breakdown Structure We use typical gantt chart break down structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … When you insert a task, the WBS is calculated displayed automatically.
Note on C7: Enter the name of the person responsible for this task.
Note on E7: Start Day Type =previous_end_cell+1 to have it follow the previous task
Note on F7: End Day Do not type anything here. Just enter the duration in the next cell to adjust this one. These are days based on a 7 days week.
Note on G7: Duration The duration is entered in calendar weekdays. Weeks are 7 days long. So 5 weeks would 5*7 = 35 days. Adjust these days in order to have the correct workdays. Also if you want to work in workdays, buy our pro version.
Note on H7: Percentage completion of task. Use this to show the percentage of completion of the task.
Note on I7: NetWorking Days This uses the excel formula Networkdays(start date, end date) in order to calculate the exact numbers of working days. Use this number to adjust your Duration. If you like to work in Working days, then we provide this feature in the pro version available on our website or by clicking on the link indicated on this sheet.
Note on J7: Calendar Days Complete Equals to: duration x %complete
Note on K7: Remaining days in calendar days.
duration for any task subtask etc... is
max(enc date of the subtasks) - start date + 1
e.g.:=MAX(F9:F14)-E8+1
Start date for any task is the
min(all subtasks)
eg: =MIN(E20:E26)
End date: is the start date + duration - 1
e.g.:=E38+G38-1
Percentage completed of a task
=SUMPRODUCT(duration of subtasks;percentages of subtask)/SUM(duration of subtasks)
eg:=SUMPRODUCT(G39:G41;H39:H41)/SUM(G39:G41)

## Pro version
The Pro version of our GANTT CHART has the following advantages:
MORE FEATURES
Fully unlocked Gantt Chart
Chose to enter the duration in workdays or in calendar days
Enter custom holidays
Enter custom weeks (6 days week for example)
Adjust all the formating (fonts size and colour)
Add your own colors to the Gantt chart bars
Add pictures and drawings
Add Sub-task Dependencies
Also
Get free updates
Use our open topic list or task management list that you can find on:
http://www.excelmadeeasy.com/open-topic-list.php

## Licence, terms of use
LICENCE agreement, terms of use, Liability, Warranty
This template is a Free Gantt Chart Template.
This document demanded many hours work and we are improving it constantly, so please help us by not distributing this document.
You are allowed to modify the GanttChart Worksheet as long as you keep it private or/and only use it with others that also purchase one copy.
You are not allowed to make public or sell this document/template and any modified version of it.
You are not allowed to put this document/template and any modified version of it on a server, public forum, free accessible server/area.
Disclaimer of Warranty: There is no warranty for the document/template. Except when otherwise stated in writing we provide the document/template “as is” without warranty of any kind, either expressed or implied, including, but not limited to, the implied warranties of merchantability and fitness for a particular purpose. the entire risk as to the quality and performance of the document/template is with you. should the document/template prove defective, you assume the cost of all necessary servicing, repair or correction.
Limitation of Liability: In no event unless required by applicable law or agreed to in writing will any copyright holder, or any other party who modifies and/or conveys the program as permitted above, be liable to you for damages, including any general, special, incidental or consequential damages arising out of the use or inability to use the document/template (including but not limited to loss of data or data being rendered inaccurate or losses sustained by you or third parties or a failure of the document/template to operate with any other programs), even if such holder or other party has been advised of the possibility of such damages.

## changes
V1:
Original
V2:
corrected error in the week day column, change the format of the number to custom jjj
allows the coloring of the cells for better visibility